## Bid Proposal - no links
ITEMIZED BID PROPOSAL
GENERAL CONSTRUCTION FOR CARY
Twin Lakes Dam Rehabilitation, Project No. PR1303 (the "Project")
ITEMIZED PROPOSAL
Item No. | Item Description | Specification Reference | Bid Quantity | Units | Unit Price | Total
1 | Construction Surveying - Site Staking and Project Survey | 21000.4 | 1 | LS |  | 0
2 | Construction Surveying - As Built Survey and Drawings | 21000.5 | 1 | LS |  | 0
3 | Traffic Control | 20000.4.A.(i) | 1 | LS |  | 0
4 | Concrete Truck Washout Pit | 21000.6 | 1 | EA |  | 0
5 | Upper Lake Draining and Filling | 21000.7 | 1 | LS |  | 0
6 | Lower Lake Draining and Filling | 21000.7 | 1 | LS |  | 0
7 | Temporary Bypass Storm Sewer (36" HDPE) | 21000.8 | 748 | LF |  | 0
8 | Temporary Outlet Protection | 21000.9 | 1 | TN |  | 0
9 | Temporary Conveyance Channel | 21000.1 | 1775 | SY |  | 0
10 | Temporary Chain Link Fence and Gates - Site Access Control | 21000.12 | 70 | LF |  | 0
11 | Tree Protection Fence | 16000.2 | 3674 | LF |  | 0
12 | Tree Protection Fence with Silt Fence | 16000.2 | 3172 | LF |  | 0
13 | Temporary Silt Fence | 16000.2 | 386 | LF |  | 0
14 | Temporary Silt Fence Outlet | 16000.2 | 11 | EA |  | 0
15 | Rock Pipe Inlet Protectiom | 21000.44 | 7 | EA |  | 0
16 | Curb Inlet Potection | 16000.2 | 4 | EA |  | 0
17 | Stone Stabilization (6" thick ABC) | 05000.3.A.(i) | 5606 | SY |  | 0
18 | Standard Temporary Stream Crossing (36") | 21000.13 | 30 | LF |  | 0
19 | Temporary Seeding | 16000.3.D.(i) | 20 | AC |  | 0
20 | Permanent Seeding with Mulch | 16000.3.D.(i) | 8 | AC |  | 0
21 | Sod | 16000.3.E.(i) | 10375 | SY |  | 0
22 | Erosion Control Matting | 16000.5 | 1500 | SY |  | 0
23 | Complete Clearing & Grubbing (area outside of lake water surface) | 03000.2.A | 9.3 | AC |  | 0
24 | Dam Embankment Tree Clearing | 21000.45 | 700 | SY |  | 0
25 | Upper Dam Riser Structure (Reinforced Concrete Riser, Box, and Wingwalls) | 06001 | 126 | CY |  | 0
26 | Lower Dam Riser Structure (Reinforced Concrete Riser, Box, and Wingwalls) | 06001 | 174 | CY |  | 0
27 | Upper Dam Outlet Structure Construction Dewatering | 21000.11 | 1 | LS |  | 0
28 | Lower Dam Outlet Structure Construction Dewatering | 21000.11 | 1 | LS |  | 0
29 | Unclassified Excavation | 4000.2 | 5440 | CY |  | 0
30 | Embankment | 4000.4 | 1230 | CY |  | 0
31 | Undercut Excavation | 4000.5 | 100 | CY |  | 0
32 | Borrow Excavation | 4000.6 | 50 | CY |  | 0
33 | Upper Lake Dam Embankment Excavation | 21000.15 | 2100 | CY |  | 0
34 | Lower Lake Dam Embankment Excavation | 21000.15 | 1900 | CY |  | 0
35 | Upper Lake Dam Embankment Fill | 21000.16 | 6320 | CY |  | 0
36 | Lower Lake Dam Embankment Fill | 21000.16 | 4550 | CY |  | 0
37 | Lower Lake Grading | 21000.17 | 18200 | CY |  | 0
38 | ASTM C33 Fine Aggregate | 21000.27 | 530 | CY |  | 0
39 | NCDOT No. 78M Coarse Aggregate | 21000.28 | 270 | CY |  | 0
40 | 6 Inch PVC Well Casing Pipe | 21000.26 | 610 | LF |  | 0
41 | Riprap | 16000.6.G | 260 | TN |  | 0
42 | Class B Riprap | 21000.35 | 1200 | TN |  | 0
43 | Class A Riprap | 21000.36 | 25 | TN |  | 0
44 | 15-inch Class III RCP Storm Sewer | 09000.5.A.(i) | 103 | LF |  | 0
45 | 18-inch Class III RCP Storm Sewer | 09000.5.A.(i) | 126 | LF |  | 0
46 | 24-inch Class III RCP Storm Sewer | 09000.5.A.(i) | 68 | LF |  | 0
47 | 15-inch Flared End Section | 09000.5.A.(ii) | 4 | EA |  | 0
48 | 18-inch Flared End Section | 09000.5.A.(ii) | 4 | EA |  | 0
49 | 24-inch Flared End Section | 09000.5.A.(ii) | 2 | EA |  | 0
50 | Upper Lake Outlet Guardrail | 21000.19 | 32 | LF |  | 0
51 | Lower Lake Outlet Guardrail | 21000.19 | 39 | LF |  | 0
52 | 20' X 20' Trash Rack | 21000.21 | 1 | EA |  | 0
53 | 9' X 9' Trash Rack | 21000.21 | 1 | EA |  | 0
54 | Low Flow Drain Inlet | 21000.22 | 2 | EA |  | 0
55 | Low Flow Drain Pipe and Fittings - 12-inch DIP | 21000.23 | 60 | LF |  | 0
56 | Low Flow Drain Gate Valve | 21000.24 | 2 | EA |  | 0
57 | Observation Well | 21000.25 | 3 | EA |  | 0
58 | Safety Rail | 21000.33 | 42 | LF |  | 0
59 | Concrete Curb and Gutter | 06000.5.A.(i) | 51 | LF |  | 0
60 | Replace Existing Sidewalk | 06000.5.A.(ii) | 240 | SY |  | 0
61 | Aggregate Base Course - Greenway Full Section | 05000.3.A.(i) | 675 | SY |  | 0
62 | Asphalt Concrete Base Course Final Grade Adjustment | 05000.3.A.(i) | 2447 | SY |  | 0
63 | Asphalt Concrete Surface Course - Greenway | 05000.3.A.(i) | 3122 | SY |  | 0
64 | Lake Normal Pool Bench Plantings | 21000.34 | 2122 | SY |  | 0
65 | Boulder | 21000.37 | 100 | TN |  | 0
66 | # 57 Stone Aggregate | 21000.29 | 62 | TN |  | 0
67 | Biomix Filter Media | 21000.38 | 367 | CY |  | 0
68 | Live Stakes | 21000.39 | 1200 | EA |  | 0
69 | Tree/Shrub - Containerized | 21000.4 | 500 | EA |  | 0
70 | Riparian Seeding | 21000.41 | 300 | SY |  | 0
71 | Pump Around Operation | 21000.42 | 20 | DY |  | 0
[5 empty] | Subtotal (Items 1-71) | 0
72 | Mobilization/Demobilization and Insurance (maximum 5% of Base Bid) |  |  |  | Mobilization & insurance (5% max) | 0
| Write out Total "Base Bid" Price (Items 1-72) |  |  |  | Total Base Bid (Items 1-72) | 0
Dollars and
Cents
Please only edit the shaded colored/highlighted cells above. All others will automatically populate based on the entries in these cells.
I acknowledge that I have received and reviewed Addendum #1 dated 2/3/2025
| Signature |  |  |  | Date
I acknowledge that I have received and reviewed Addendum #2 dated 2/7/2025
| Signature |  |  |  | Date
NOTE: PROPOSAL SIGNATURE REQUIRED ON PAGE 00300-12]. ALL PROPOSALS MUST BE PROPERLY EXECUTED TO BE CONSIDERED A VALID BID.